## MOBILE SS
Negin Bushehr 63/20KV Mobile SS |  | send(RevZ) | receive(RevZ) | وضعيت | send(RevA) | receive(RevA) | وضعيت | send(RevB) | receive(RevB) | وضعيت | send(RevC) | receive(RevC) | وضعيت | send(RevD) | receive(RevD) | وضعيت | send(RevE) | receive(RevE) | وضعيت | send(RevF) | receive(RevF) | وضعيت
|  | LETTER | LETTER |  | LETTER | LETTER |  | LETTER | LETTER |  | LETTER | LETTER |  | LETTER | LETTER |  | LETTER | LETTER |  | LETTER | LETTER
GENERAL | LIST OF DOCUMENT | 1404/08/14 | 1404/09/04 | A.N
|  | 1404/ES/S/3323 | 04/2001410/2979
| GENERAL SINGLE LINE DIAGRAM DIAGRAM | 1404/09/09 | 1404/09/15 | A | 1404/11/06 | 1405/01/29 | A | 1405/03/23 | 1405/03/25 | A
|  | 1404/ES/S/3644 | 04/2001410/3131 |  | 1404/ES/S/4457 | 05/2001410/121 |  | 1405/ES/S/1648 | 05/2001410/896
| PROT & CONTROL SINGLE LINE DIAGRAM | 1404/02/09 | 1404/09/15 | A.N | 1404/09/1404 | 1404/09/23 | A.N | 1404/10/07 | 1404/10/14 | A | 1405/02/16 | 1405/06/01 | CM | 1405/07/13
|  | 1404/ES/S/3644 | 1404/ES/S/3644 |  | 1404/ES/S/3844 | 04/2001410/3277 |  | 1404/ES/S/4137 | 04/2001410/3552 |  | 1405/ES/S/1301 | 05/2001410/1888 |  | 1405/ES/S/2783
| LVAC SINGLE LINE DIAGRAM | 1404/10/23 | 1404/11/01 | CM
|  | 1404/ES/S/4349 | 04/2001410/3810
| 110VDC SINGLE LINE DIAGRAM | 1404/09/24 | 1404/10/06 | CM | 1404/10/17 | 1404/10/22 | A.N | 1404/11/04 | 1404/11/05 | A
|  | 1404/ES/S/3899 | 04/2001410/3458 |  | 1404/ES/S/4260 | 04/2001410/3651 |  | 1404/ES/S/4433 | 04/2001410/3847
48VDC SINGLE LINE DIAGRAM
| TRIP TABLE | 1404/09/18 | 1404/09/23 | A.N | 1404/10/14 | 1404/10/16 | A.N | 1404/10/20 | 1405/02/20 | HOLD
|  | 1404/ES/S/3845 | 04/2001410/3275 |  | 1404/ES/S/4222 | 04/2001410/3590 |  | 1404/ES/S/4276 | 05/2001410/399
| ALARM & SIGNAL LIST | 1404/10/22 | 1404/11/01 | CM
|  | 1404/ES/S/4335 | 04/2001410/3808
PANEL ARRANGEMENT
| CONTROL LOGIC DIAGRAM | 1404/09/18 | 1404/09/23 | CM | 1404/10/14 | 1404/10/17 | CM | 1404/11/04 | 1404/11/05 | A
|  | 1404/ES/S/3843 | 02/2001410/3274 |  | 1404/ES/S/4221 | 04/2001410/3606 |  | 1404/ES/S/4436 | 04/2001410/3846
LV | MV PANEL FRONT VIEW
| PROTECTION PANEL FRONT VIEW | 1404/09/18 | 1404/09/23 | A.N | 1404/10/07 | 1404/10/14 | A
|  | 1404/ES/S/3833 | 04/2001410/3294 |  | 1404/ES/S/4140 | 04/2001410/3574
| CONTROL PANEL FRONT VIEW | 1404/09/18 | 1404/09/23 | CM | 1404/10/07 | 1404/10/14 | CM | 1404/10/22
|  | 1404/ES/S/3832 | 04/2001410/3296 |  | 1404/ES/S/4139 | 04/2001410/3573 |  | 1404/ES/S/4336
| AVR PANEL FRONT VIEW | 1404/09/19 | 1404/09/25 | CM | 1404/10/07 | 1404/10/14 | CM | 1404/10/20
|  | 1404/ES/S/3867 | 04/2001410/3332 |  | 1404/ES/S/4141 | 04/2001410/3553 |  | 1404/ES/S/4277
| METERING PANEL FRONT VIEW | 1404/09/18
1404/ES/S/3846
| HVI & YV PANEL FRONT VIEW | 1404/09/19
1404/ES/S/3866
| LVAC PANEL FRONT VIEW | 1404/10/23 | 1404/11/01 | CM
|  | 1404/ES/S/4348 | 04/2001410/3812
| LVDC PANEL FRONT VIEW | 1404/10/23 | 1404/11/01 | CM
|  | 1404/ES/S/4350 | 04/2001410/3811
| CT CALCULATION | 1404/10/20 | 1405/02/20 | HOLD
|  | 1404/ES/S/4275 | 05/2001410/397
CVT CALCULATION
LVAC CABLE CALCULATION
LVDC CABLE CALCULATION
110VDC BATTERY & CHARGER SPECIFICATION
COMMUNICATION SYSTEM SPECIFICATION
48VDC BATTERY & CHARGER SPECIFICATION
| PROTECTION RELAY & ACCESSORIES LIST & ORDER CODE | 1404/10/14 | 1405/02/20 | HOLD
|  | 1404/ES/S/4223 | 05/2001410/400
CONTROL SCHEMATIC DIAGRAM
PROTECTION SCHEMATIC DIAGRAM
MARSHALLING SCHEMATIC DIAGRAM
20KV INCOMING SCHEMATIC DIAGRAM
20KV OUTGOING SCHEMATIC DIAGRAM
20KV CAPACITOR BANK SCHEMATIC DIAGRAM
LVAC SCHEMATIC DIAGRAM
LVDC 110V SCHEMATIC DIAGRAM
LVDC 48V SCHEMATIC DIAGRAM
YV/MR SCHEMATIC DIAGRAM
SCADA RTU SCHEMATIC DIAGRAM
CABLE LIST & CABLE CONNECTION TABLE
COMMUNICATION OVERVIEW
| SUBSTATION LAYOUT & SECTION DRAWING | 1404/09/09 | 1404/09/15 | A.N | 1405/02/16 | 1405/03/10 | RM | 1405/03/23 | 1405/03/25 | CM | 1405/04/07 |  |  | 1405/04/31
|  | 1404/ES/S/3644 | 04/2001410/3131 |  | 1404/ES/S/1300 | 05/2001410/690 |  | 1405/ES/S/1647 | 05/2001410/895 |  | 1405/ES/S/1799 |  |  | 1405/ES/S/2078
EARTHING SYSTEM PLAN
EARTHING SYSTEM DETAILS
CLAMP AND FITTING LOCATION & DETAIL DRAWING
CABLE SUPPORT PLAN & DETAIL DRAWING
OUTDOOR LIGHTING PLAN & DETAIL
INDOOR LIGHTING PLAN & DETAIL
ELECTRICAL BUSWORK CALCULATION
MECHANICAL BUSWORK CALCULATION
OUTDOOR LIGHTING CALCULATION
INDOOR LIGHTING CALCULATION
MV CABLE CALCULATION
| MTO AND TECHNICAL DATA SHEET FOR CIRCUIT BREAKER | 1404/08/14 | 1404/09/04 | A.N | 1404/09/17 | 1404/09/23 | A
|  | 1404/ES/S/3323 | 04/2001410/2979 |  | 1404/ES/S/3822 | 04/2001410/3279
| MTO AND TECHNICAL DATA SHEET FOR DISCONNECTOR / EARTH SWITCH | 1404/08/14 | 1404/09/04 | CM | 1404/09/17 | 1404/09/23 | A
|  | 1404/ES/S/3323 | 04/2001410/2979 |  | 1404/ES/S/3820 | 04/2001410/3280
| MTO AND TECHNICAL DATA SHEET FOR SURGE ARRESTER & COUNTER | 1404/08/14 | 1404/09/04 | A.N | 1404/09/16 | 1404/09/19 | A
|  | 1404/ES/S/3323 | 04/2001410/2979 |  | 1404/ES/S/3787 | 04/2001410/3242
| MTO AND TECHNICAL DATA SHEET FOR LINE TRAP AND LMU | 1404/08/14 | 1404/09/04 | A.N
|  | 1404/ES/S/3323 | 04/2001410/2979
MTO AND TECHNICAL DATA SHEET FOR PI, CONDUCTOR & SHIELD WIRE
| MTO AND TECHNICAL DATA SHEET FOR CVT | 1404/08/14 | 1404/09/04 | A.N | 1404/09/17 | 1404/09/23 | A
|  | 1404/ES/S/3323 | 04/2001410/2979 |  | 1404/ES/S/3819 | 04/2001410/3281
| MTO AND TECHNICAL DATA SHEET FOR CT | 1404/08/14 | 1404/09/04 | CM | 1404/09/17 | 1404/09/23 | A.N
|  | 1404/ES/S/3323 | 04/2001410/2979 |  | 1404/ES/S/3821 | 04/2001410/3278
MTO AND TECHNICAL DATA SHEET FOR POWER TRANSFORMER & AUXILIARY TRANSFORMER
| MTO AND TECHNICAL DATA SHEET FOR EARTHING SYSTEM | 1404/08/14 | 1404/09/04 | CM
|  | 1404/ES/S/3323 | 04/2001410/2979
HV | KEY PLAN OF FOUNDATION
20kV SWITCHGEAR & CONTROL CONNEX PLAN & VIEWS & SECTIONS
EQUIPMENT SUPPORT STRUCTURE DETAIL DRAWINGS
STAIR & HANDRAIL OF 20KV & CONTROL CONNEX DETAIL DRAWINGS
TRAILER CHASSIS DRAWING
STRUCTURAL DRAWING OF GANTRY BEAM (CONCRETE COLUMN & STEEL BEEM)
BOUNDARY FENCE DRAWINGS